Instructional Video Production

Proposal for Philippine Air Force

Prepared for:

LTC. Christna DC Bechayda PAF
Assistant Commandant PAFTSS

Prepared by:

Elmer Epistola
Founder & CEO
Acadev Technologies, Inc.

February 25, 2026

ACADEV TECHNOLOGIES INC.  Proposal for Philippine Air Force

Prepared for:	LTC. Christna DC Bechayda PAF

Assistant Commandant PAFTSS

Prepared by:	Elmer Epistola – Founder & CEO

Acadev Technologies Inc.

# PROGRAM DESCRIPTION

# This is a proposal for the Philippine Air Force (PAF) to convert existing subject course materials from static PDF or text format into dynamic, instruction-ready structured training videos.

# At present, PDF-based materials primarily serve as reference documents. While they contain valuable information, they are not always optimized for instructional delivery, visual engagement, or standardized classroom facilitation. By transforming these materials into professionally designed videos, the content becomes more structured, visually guided, and easier for instructors to deliver effectively.

# This initiative aims to modernize instructional delivery by integrating clear visual layouts, simplified content flow, diagrams, highlights, and structured learning segments that support better understanding. Converting materials into video format also enhances learner engagement, as personnel can follow organized lessons that emphasize key concepts rather than dense text blocks.

# Furthermore, this transformation supports the standardization of training materials across units. With unified video modules, instructors can deliver consistent lessons regardless of location through their internal learning management system, reducing variations in interpretation and ensuring alignment with official doctrine and procedures.

# Ultimately, this project contributes to mission readiness by strengthening knowledge retention, improving clarity of instruction, and creating reusable digital learning assets that can be updated as policies and operational requirements evolve.

## PROJECT OBJECTIVES

The development of instructional training videos under this proposal aims to achieve the following objectives:

- Improve instructional effectiveness
Structured presentations and guided video content enable instructors to deliver lessons more clearly and systematically, enhancing overall teaching quality.

- Increase engagement and knowledge retention
Visual elements, organized content flow, and multimedia delivery help personnel better understand key concepts and retain critical operational information.

- Support blended and remote learning
Digital formats allow courses to be delivered in classroom settings, virtual platforms, or self-paced environments, providing greater flexibility in training deployment.

- Ensure consistency across training units
Standardized materials promote uniform delivery of doctrine and procedures across all units and training centers.

- Preserve critical knowledge for posterity

Converting course materials into durable digital video format safeguards essential institutional knowledge and operational procedures against loss, degradation, or obsolescence over time.

- Create future-proof digital assets for ongoing use
Editable and reusable digital materials can be updated as policies and operational requirements evolve, ensuring long-term value and sustainability.

- SCOPE OF WORK

Approved course materials will be converted into structured instructional videos. Existing PDF content will be carefully restructured to improve clarity, logical flow, and instructional sequencing for the video medium. Each subject will be transformed into a professionally produced video that incorporates appropriate visuals, charts, diagrams, and highlighted key points to support effective delivery. This includes developing a clear script based on the provided content to ensure accurate and organized presentation. Videos may be slide-based or include appropriate animations to enhance understanding.

Optional voice-over narration can be incorporated to guide learners through the material. Each video may also include standardized intro and outro branding, if required, to ensure alignment with institutional branding and standards. Final outputs will be delivered in high-resolution format, ready for internal distribution or integration into training platforms. All completed video project files will be delivered in fully editable formats, allowing future updates and reuse for subsequent training cycles.

- DELIVERABLES

- High-resolution training videos 
Final outputs will be provided in high-resolution format suitable for classroom presentation, internal distribution, or integration into digital learning platforms.

- Organized digital archive of all materials
All completed files will be compiled and arranged in a structured digital archive for easy access, storage, and future reference.

- Minor revisions support after submission
Reasonable minor revisions will be accommodated after initial submission to ensure alignment with approved content and formatting standards.

- PROPOSED INVESTMENT

| SERVICE | RATE |
| --- | --- |
| PDF to Video Production | ₱18,000 – ₱30,000 per 10-minute video (depending on number of videos ordered, ease of agreed-upon workflow, and quality specifications) |

- PROJECT TIMELINE

- Initial Planning & Material Review: 3–5 working days
The project will begin with a detailed review of the course material provided, including content assessment, clarification of requirements, and confirmation of output specifications for video production.

- Video Production: 5-15 working days per video
Video  production will be a multi-stage process to ensure a high-quality, instructionally effective final product. This includes the following steps:

  - Content Restructuring & Scripting

The source PDF materials will be analyzed to reorganize information for a linear video format. A detailed script will be developed  to ensure clarity and logical sequencing.

  - Visual & Asset Acquisition and Creation

All essential and technical visual elements, including PAF’s standard background video, will be provided by PAF, except for noncritical generic images inserted simply for visual appeal, which will be created or sourced by Acadev.

  - Voice-Over Narration (Optional)

Preapproved  synthetic vocies will be used for voice-over narration. The audio will be carefully edited for clarity, pacing, and tone to ensure it complements the visual elements and guides the learner effectively.

  - Video Editing & Animation

The visuals, narration, and background audio will be synchronized in the editing phase. Motion graphics and animations will be added to emphasize key points and create a dynamic, polished presentation that transforms static content into an engaging learning experience.

  - Review & Revisions

A draft version of the video will be provided for client review and feedback. Necessary revisions will be implemented to ensure accuracy and alignment with the PAF's requirements.

  - Final Rendering & Delivery

The final video will be rendered in high-resolution format, including versions with standardized intro/outro branding if requested. All associated project files will also be delivered in editable formats to facilitate future updates.

Note: The overall timeline may be adjusted based on the volume, depth, and technical complexity of the materials provided by the Philippine Air Force. The video production duration depends on the final length and complexity of the course material.

- NEXT STEPS

- PAF provides PDF course materials, and specifications.
The Philippine Air Force will submit the official PDF course materials that require video prodcution along with any specific formatting, branding, or technical requirements for the project.

- Review materials and confirm requirements.
A comprehensive review of the submitted content will be conducted to clarify scope, confirm deliverables, and align expectations on structure, format, and timelines.

- Provide final quotation and timeline.
Based on the volume and complexity of the materials, a specific quotation for each video ordered will be submitted and confirmed production schedule will be issued for approval.

- Begin development and deliver digital outputs.
Upon approval, video development will commence, followed by structured progress updates and final delivery of the completed training videos. Essential technical or specialized video assets needed for video production will be provided by PAF.

VIII.    CLOSING

We look forward to supporting the Philippine Air Force in strengthening its digital training capabilities by transforming traditional course materials into structured, technology-enabled learning resources. Through modern and efficient instructional solutions, this initiative aims to enhance knowledge delivery, improve learning outcomes, and contribute to sustained mission readiness across all training units.



Respectfully submitted,

Elmer B. Epistola
FOUNDER & CEO
Acadev Technologies Inc.