LAN-Based Aircraft Maintenance Training Platform Proposal for

the Philippine Air Force (PAF)

Prepared for:  The Philippine Air Force (PAF)

Prepared by:

Elmer Epistola, CEO, Acadev Technologies, Inc.

May 16, 2025

LAN-Based Aircraft Maintenance Training Platform

Proposal for the Philippine Air Force

### 1. EXECUTIVE SUMMARY

Acadev Technologies, Inc. is excited to propose the design and development of a LAN-based Aircraft Maintenance Training Platform specifically tailored to the operational needs of the Philippine Air Force (PAF). The platform is envisioned as a secure, interactive learning environment that elevates technical training standards through engaging modular lessons, automated quiz generation, augmented reality (AR) features, and competency-based assessments  - all accessible within a self-contained local network.

By operating entirely offline, the system guarantees continuous training capabilities even in isolated or high-security bases where internet access is restricted or impractical. Moreover, it upholds data confidentiality and operational integrity, aligning with the Air Force’s security protocols. Designed to simulate real-world maintenance procedures and knowledge checks, the platform empowers airmen to train independently, track progress, and reinforce mission-critical skills without relying on traditional classroom constraints.

Incorporating modern instructional design, secure LAN architecture, and compliance with ICT standards, this solution supports the PAF’s broader mission to cultivate technically proficient, self-reliant personnel capable of sustaining airworthiness and readiness across all units.

### 2. PROJECT OBJECTIVES

2.1. To digitize and streamline maintenance training within PAF facilities

The project seeks to modernize the aircraft maintenance training process by transitioning from manual, paper-based methods to a fully digital platform. This will enhance accessibility, standardize instruction across units, and improve overall training efficiency.

2.2. To provide interactive and modular e-learning content

The system will deliver structured training materials through a modular format that includes e-books, videos, and augmented reality (AR) content. This approach allows learners to study at their own pace while promoting engagement and long-term retention of technical knowledge.

2.3. To assess trainee performance through integrated quizzes and reporting tools

An automated assessment system will be built into the platform, enabling trainers to monitor and evaluate trainee progress through quizzes and analytics. This feature will support timely feedback, targeted instruction, and data-driven decision-making for instructors and leadership.

2.4. To maintain security and performance through a LAN-based setup with no internet dependence

By operating entirely within a secure local area network (LAN), the platform ensures that all training activities and data remain protected from external threats. This architecture supports mission readiness by enabling continuous access to training resources, even in isolated or high-security environments.

### 3. SCOPE OF WORK

3.1. System Features

- User Management: Admin, Instructor, and Trainee roles with unique access controls

- Training Modules: Aircraft maintenance lessons in multimedia format (text, video, 2D image)

- Quiz Giver: Auto-generating quizzes with multiple question types and difficulty levels

- Augmented Reality: AR-enabled educational content (up to 30 augmentations included in this project proposal)

- Progress Tracking: Score report card, completion records, and performance analytics

- LAN Deployment: Fully offline setup with local server support

- Data Backup & Sync: Manual or periodic local data backup for system safety

- Responsive Design: Usable on desktop and tablet devices within the local network

3.2. Security Standards

- Authentication and role-based access

- Local firewall configuration and patch management protocols

- Data encryption at rest and in transmission within the LAN

4. TECHNICAL REQUIREMENTS

4.1 Hardware (only the server is included in this project)

- 1 local server (Intel Core i7 (12th Gen or later) or AMD Ryzen 7 (8 cores, 16 threads), 32GB RAM, 1TB SSD) – already included in this project

- LAN set-up (already in the PAF ICT Lab; networking and security set-up and related aspects will be handled by PAF’s ICT team)

- Workstations or tablets for trainee access (to be provided by PAF)

4.2 Software (all are already included in this project)

- Custom-built web-based system (HTML5, PHP, MySQL)

- Local server OS (Windows Server)

- Backup software and logging tools

### 5. PROJECT MILESTONES AND BILLING

Total Project Cost: PHP785,000.00

In accordance with ICT standards based on DICT Circular 2020-002 and ISO/IEC 29110, the project will be executed in six structured phases, each with specific deliverables, timeframes, and associated costs:

| Phase | Deliverable | Timeframe | Amount (PHP) |
| --- | --- | --- | --- |
| 1. Inception | Project planning, scope finalization, stakeholder alignment, and requirements analysis | 2 weeks | PHP 314,000.00 (Down payment required to purchase PC and software before project commencement) |
| 2. System Design | UI/UX design mockups, database schema creation, LAN architecture and security blueprint | 2 weeks |  |
| 3. System Development | Core system build including learning management backend, user access control, and quiz engine | 8 weeks | PHP 157,000.00 |
| 4. Content Development | Integration of training modules: videos, documents, quizzes, AR features, and simulations | 10 weeks | PHP 157,000.00 |
| 5. Testing & QA | Full system testing, content verification, LAN configuration tests, and training simulation | 2 weeks | PHP 157,000.00 |
| 6. Deployment & Training | Final deployment, on-site configuration, user training, and full documentation turnover | 2 weeks |  |

Total Duration: 26 weeks (6.5 months)

Notes:

1. Invoices will be issued upon formal approval of each milestone, and payment will be expected within two weeks following invoice issuance.

2. All the content (texts, images,videos, animations, and AR augmentations) to be used in the development of this training platform will be provided by PAF.

3. Additional fees may apply to customized videos and other forms of content to be produced by Acadev.

### 6. MAINTENANCE & SUPPORT

To ensure the stability and effectiveness of the Aircraft Maintenance Training Platform after deployment, the following support policy will be in place:

#### 6.1 Three (3) Months Post-Deployment Warranty Support

For a period of three months following deployment, the development team will provide free warranty support focused on system reliability and user adaptation. This includes:

- Remote technical assistance via Zoom for minor issues, user guidance, and troubleshooting

- Minor bug fixes and performance adjustments provided remotely through PAF-side manual file overwrites in close coordination with the PAF’s ICT team

- System diagnostics support, including guided steps via Zoom for resolving minor issues

- Onsite support for major failures that can not be resolved remotely even after close coordination the PAF’s ICT team

In the highly unlikely event that a critical failure that cannot be resolved remotely or onsite occurs, the affected system will have to be pulled out of PAF’s lab for transport to the developer’s office where all diagnostic tools and expertise are available for in-depth inspection and repair.

#### 6.2 Post-Warranty Support (On Request)

After the warranty period, support will be available on a case-by-case basis:

- Technical support, content updates, and repairs may be requested and will be quoted individually

- All post-warranty servicing must be coordinated in advance, with the system returned to the developer’s office if required

- Remote consultation or diagnostics may be provided but corresponding fees may apply

This structure offers the Philippine Air Force a clear, no-surprise support path while maintaining operational flexibility in a secure, offline environment.

### 7. CONCLUSION

This project stands as a strategic investment in the future of the Philippine Air Force's technical training capabilities. By adopting a LAN-based solution, we are ensuring that aircraft maintenance education is delivered with the highest standards of security, flexibility, and scalability. This modernized approach will not only improve training efficiency but also future-proof the PAF’s educational infrastructure, allowing it to adapt seamlessly to evolving technical requirements.

Our commitment is to provide a robust, high-quality system that meets the stringent demands of the Philippine Air Force. We will deliver a solution that is not just compliant with industry standards, but also specifically tailored to the unique operational and security needs of the PAF, ensuring that the platform will be both effective and sustainable for years to come.